## 1. Remediation Roadmap
Remediation Roadmap — HealthNet Ireland Ltd
All 48 gaps from Task 4, organised into 3 phases: quick wins & policy fixes (0-3mo) -> process, training & vendor reviews (3-6mo) -> strategic, tooling & cultural change (6-12mo)
Ref | Domain | Remediation Action | Priority | Phase | Timeframe | Effort | Owner
GOV-01 | Governance & Accountability | Present risk-management measures to the board for formal sign-off; record approval in board minutes. | High | Phase 1 | 0-3 months | Low | CEO
GOV-02 | Governance & Accountability | Build a quarterly cyber risk dashboard (incidents, top risks, training %, patching status) as a standing board agenda item. | High | Phase 1 | 0-3 months | Low | IT Manager
GOV-03 | Governance & Accountability | Establish an annual structured cybersecurity training programme for all board members, with attendance tracked. | Medium | Phase 2 | 3-6 months | Medium | CEO
GOV-04 | Governance & Accountability | Enforce annual training completion to 100%, with automated reminders and escalation for non-completers. | Medium | Phase 2 | 3-6 months | Medium | HR
RSK-01 | Risk Analysis & Policies | Review and re-approve the Information Security Policy; establish an annual review cycle going forward. | Medium | Phase 1 | 0-3 months | Low | IT Manager
RSK-02 | Risk Analysis & Policies | Adopt a risk assessment methodology (e.g. ISO 27005-aligned) and run the first full risk assessment. | High | Phase 1 | 0-3 months | Medium | IT Manager
RSK-03 | Risk Analysis & Policies | Build and populate a risk register with owners, scores, and treatment decisions; review quarterly. | High | Phase 1 | 0-3 months | Medium | IT Manager
RSK-04 | Risk Analysis & Policies | Extend risk assessments to cover physical and environmental hazards (server room access, fire, power). | Medium | Phase 2 | 3-6 months | Medium | IT Manager
INC-01 | Incident Handling | Develop a full incident response plan: severity classification, roles, escalation paths, and playbooks for ransomware/data breach scenarios. | High | Phase 2 | 3-6 months | High | IT Manager
INC-02 | Incident Handling | Consolidate incident detection into a dedicated central incident register, separate from general IT tickets. | Medium | Phase 2 | 3-6 months | Medium | IT Manager
INC-03 | Incident Handling | Define incident response roles (incl. a deputy) and establish an out-of-hours on-call rota. | Medium | Phase 2 | 3-6 months | Low | IT Manager
INC-04 | Incident Handling | Run the first tabletop exercise simulating a realistic incident scenario; capture lessons learned. | Medium | Phase 3 | 6-12 months | Medium | IT Manager
INC-05 | Incident Handling | Establish a post-incident review process, with corrective actions tracked to closure. | Medium | Phase 2 | 3-6 months | Low | IT Manager
BCM-02 | Business Continuity & Backup | Implement a logically isolated (separate-account or immutable) backup copy; schedule quarterly restore tests. | High | Phase 1 | 0-3 months | Medium | Platform Lead
BCM-03 | Business Continuity & Backup | Finalise the BC/DR plan; agree RTO/RPO with the business and reflect in customer SLAs. | High | Phase 2 | 3-6 months | High | IT Manager
BCM-04 | Business Continuity & Backup | Define a crisis management team, decision authority, and communications plan for major incidents. | Medium | Phase 2 | 3-6 months | Medium | CEO
BCM-05 | Business Continuity & Backup | Test regional failover in a controlled exercise; validate RTO/RPO against the finalised plan. | Medium | Phase 3 | 6-12 months | Medium | Platform Lead
SCM-01 | Supply Chain Security | Risk-rank the supplier inventory; identify and flag critical ICT suppliers. | Medium | Phase 2 | 3-6 months | Low | Ops
SCM-02 | Supply Chain Security | Add a security schedule, audit rights, and 24-hour incident notification clause to all critical supplier contracts at renewal. | High | Phase 2 | 3-6 months | Medium | Legal
SCM-03 | Supply Chain Security | Introduce a due-diligence questionnaire for onboarding new suppliers, with periodic re-assessment. | Medium | Phase 2 | 3-6 months | Medium | Ops
SCM-04 | Supply Chain Security | Once the risk register exists, formally assess and log supply-chain risk from the 3 critical software suppliers. | Medium | Phase 3 | 6-12 months | Low | IT Manager
SDA-01 | Secure Development & Vulnerability Handling | Adopt a secure development standard (OWASP-aligned) with mandatory security review gates in the SDLC. | Medium | Phase 2 | 3-6 months | Medium | Dev Lead
SDA-02 | Secure Development & Vulnerability Handling | Deploy authenticated vulnerability scanning; adopt CVSS-based remediation SLAs (Critical 7 days, High 30 days). | Medium | Phase 2 | 3-6 months | Medium | Platform Lead
SDA-03 | Secure Development & Vulnerability Handling | Publish a coordinated vulnerability disclosure policy and security.txt with a designated contact. | Low | Phase 1 | 0-3 months | Low | Dev Lead
SDA-04 | Secure Development & Vulnerability Handling | Schedule an independent annual penetration test; close all open medium-severity findings from 2024. | Medium | Phase 2 | 3-6 months | Medium | Platform Lead
EFF-01 | Effectiveness Assessment | Establish an annual internal control self-assessment programme with defined KPIs. | Medium | Phase 3 | 6-12 months | Medium | IT Manager
EFF-02 | Effectiveness Assessment | Report control effectiveness results to the board alongside the cyber risk dashboard. | Medium | Phase 3 | 6-12 months | Low | IT Manager
EFF-03 | Effectiveness Assessment | Build a findings and corrective-action register, tracking all issues to closure. | Medium | Phase 3 | 6-12 months | Low | IT Manager
HYG-02 | Cyber Hygiene & Training | Introduce periodic phishing simulations; enforce 100% training completion. | Medium | Phase 2 | 3-6 months | Medium | HR
HYG-03 | Cyber Hygiene & Training | Deliver role-specific training: secure coding (OWASP Top 10) for developers, privileged-access training for admins. | Low | Phase 2 | 3-6 months | Medium | Dev Lead
HYG-04 | Cyber Hygiene & Training | Introduce annual re-attestation of the Acceptable Use Policy for all staff. | Low | Phase 1 | 0-3 months | Low | HR
CRY-01 | Cryptography | Document a cryptography policy formalising existing encryption practice (algorithms, TLS baseline, key lifecycle). | Low | Phase 1 | 0-3 months | Low | Platform Lead
CRY-03 | Cryptography | Deploy a secrets management tool; purge hardcoded secrets from repositories; define a rotation schedule. | High | Phase 1 | 0-3 months | Medium | Platform Lead
HRA-01 | HR, Access Control & Assets | Formalise the joiner-mover-leaver process with HR-triggered same-day access revocation; immediately audit and remove orphaned accounts. | High | Phase 1 | 0-3 months | Low | HR
HRA-02 | HR, Access Control & Assets | Implement an RBAC model with an approval workflow; remove standing production admin access from developers. | High | Phase 2 | 3-6 months | Medium | Platform Lead
HRA-03 | HR, Access Control & Assets | Introduce quarterly access recertification for production/privileged systems, annually for others. | Medium | Phase 2 | 3-6 months | Low | IT Manager
HRA-04 | HR, Access Control & Assets | Deploy asset management tooling; build a full inventory of hardware, software, and information assets with owners. | Medium | Phase 3 | 6-12 months | Medium | IT Manager
HRA-05 | HR, Access Control & Assets | Define a secure disposal procedure (certified wipe/destruction); clear the existing device backlog. | Low | Phase 1 | 0-3 months | Low | IT Manager
MFA-01 | Authentication & Secure Comms | Enforce MFA immediately on the AWS console and the SaaS admin portal. | High | Phase 1 | 0-3 months | Low | Platform Lead
MFA-02 | Authentication & Secure Comms | Make platform MFA default-on for all users; agree an enforced rollout plan with hospital customers. | Medium | Phase 3 | 6-12 months | Medium | Product
MFA-03 | Authentication & Secure Comms | Define a policy on secure channels for communicating sensitive/incident information. | Low | Phase 2 | 3-6 months | Low | IT Manager
MFA-04 | Authentication & Secure Comms | Establish an out-of-band emergency communication channel and a printed break-glass contact list. | Medium | Phase 1 | 0-3 months | Low | IT Manager
REP-01 | Incident Reporting | Draft a 24-hour early warning procedure and template; record CSIRT-IE contact details; brief on-call staff. | High | Phase 1 | 0-3 months | Low | DPO
REP-02 | Incident Reporting | Draft a 72-hour notification procedure, distinct from but coordinated with the GDPR Art. 33 process. | High | Phase 1 | 0-3 months | Low | DPO
REP-03 | Incident Reporting | Build a final incident report template, populated from the post-incident review process once established. | Medium | Phase 2 | 3-6 months | Low | DPO
REP-04 | Incident Reporting | Define clear significance criteria (service downtime thresholds, confirmed data breach) mapped to platform impact. | High | Phase 1 | 0-3 months | Low | DPO
REG-01 | Registration & Regulator Engagement | Prepare entity registration details, ready for submission once the Irish registration portal opens. | High | Phase 1 | 0-3 months | Low | DPO
REG-02 | Registration & Regulator Engagement | Assign a named owner to monitor Irish NIS2 transposition and NCSC guidance developments. | Low | Phase 1 | 0-3 months | Low | DPO

## 2. Roadmap Summary
Roadmap Summary — HealthNet Ireland Ltd
Live counts calculated from Sheet '1. Remediation Roadmap'
GAPS BY PHASE
Phase | Timeframe | Total | High Priority | % of All Gaps
Phase 1 | 0-3 months | 19 | 12 | 39.58%
Phase 2 | 3-6 months | 21 | 4 | 43.75%
Phase 3 | 6-12 months | 8 | 0 | 16.67%
WORKLOAD BY OWNER
Owner | Total Actions | Phase 1 | Phase 2 | Phase 3
IT Manager | 20 | 6 | 8 | 6
Platform Lead | 8 | 4 | 3 | 1
Dev Lead | 3 | 1 | 2 | 0
CEO | 3 | 1 | 2 | 0
HR | 4 | 2 | 2 | 0
Ops | 2 | 0 | 2 | 0
Legal | 1 | 0 | 1 | 0
Product | 1 | 0 | 0 | 1
DPO | 6 | 5 | 1 | 0
KEY TAKEAWAY
The IT Manager owns roughly 40% of all 48 remediation actions across every phase — a direct consequence of HealthNet having no dedicated security/GRC function today. This single finding is itself a board-level recommendation: without a dedicated hire (or this engagement), the roadmap's own timeline is at risk from one person's bandwidth.